## 📊 Executive Dashboard
OBSERVABILITY PLATFORM ¦ TEST CLOSURE REPORT
Release: v1.0 │ MVP-1 & MVP-2 │ Phases: ST · SIT │ Go / No-Go Decision
Prepared by: QA Lead / Test Manager | [6 empty] | Date: [Enter Date] Version: 1.0
▶ GO / NO-GO VERDICT: [ GO ✔ ] ¦ IT Testing Closure: COMPLETE ¦ Status: READY FOR UAT COMMENCEMENT
Total Test Cases |  | Executed |  | Passed |  | Failed |  | Blocked |  | Pass %
624 |  | 624 |  | 602 |  | 19 |  | 3 |  | 96.4744
PHASE-WISE TEST EXECUTION SUMMARY
Phase | MVP Scope | Total TCs | Executed | Passed | Failed | Blocked | Not Run | Pass % | Defects Raised | Defects Closed | Status
System Testing (ST) | MVP-1 & MVP-2 | 443 | 443 | 427 | 14 | 2 | 0 | 0 | 16 | 12 | PASS
System Integration Testing (SIT) | MVP-1 & MVP-2 | 181 | 181 | 175 | 5 | 1 | 0 | 0 | 6 | 6 | PASS
TOTAL / COMBINED | Both MVPs | 0 | 624 | 624 | 602 | 19 | 3 | 0 | 0 | 22 | —
MVP READINESS STATUS
MVP | Modules Covered | Test Coverage % | Defects (P1/P2) | Defects (P3/P4) | Deferred Issues | UAT Ready | Recommendation
MVP-1: Data Ingestion & Pipeline | Collector, Parser, Storage, API Gateway | 95.2381 | [Enter] | [Enter] | 14 | YES ✔ | GO
MVP-2: Dashboards & Alerting | Visualization, Alert Engine, Notification, RBAC | 95.8333 | [Enter] | [Enter] | 0 | YES ✔ | GO
QUALITY GATE CHECKLIST (All criteria must be MET for GO decision)
# | Quality Gate Criterion | Threshold | Actual | Status | Owner
1 | Pass % ≥ 95% across ST + SIT | ≥ 95% | 96.4744 | MET ✔ | QA Lead
2 | Zero open P1 / Critical defects | 0 open P1 | 0 | MET ✔ | Dev Lead
3 | Zero open P2 / Major defects | 0 open P2 | 0 | MET ✔ | Dev Lead
4 | Test execution ≥ 98% of planned TCs | ≥ 98% | 100 | MET ✔ | QA Lead
5 | All ST exit criteria signed off | Yes | YES | MET ✔ | Test Manager
6 | All SIT exit criteria signed off | Yes | YES | MET ✔ | Test Manager
7 | Regression suite fully executed | Yes | YES | MET ✔ | Automation Lead
8 | Performance benchmarks met | Latency < 200ms | YES | MET ✔ | Perf Engineer
9 | Security scans – no High/Critical findings | 0 High/Crit | YES | MET ✔ | SecOps
10 | All deferred issues have release assignment | Yes | YES | MET ✔ | PM

## 📌 Entry & Exit Criteria
ENTRY & EXIT CRITERIA — ST · SIT PHASES
All criteria must be verified and signed-off before phase commencement / closure
ST — ENTRY CRITERIA
# | Criteria ID |  | Owner | Date Verified | Status
1 | EC-ST-01 | Test environment (Observability Platform) fully provisioned and stable |  | QA Lead | [Enter Date] | MET ✔
2 | EC-ST-02 | All MVP-1 & MVP-2 code modules deployed to ST environment (build sign-off) |  | Dev Lead | [Enter Date] | MET ✔
3 | EC-ST-03 | Test data sets prepared (log streams, metrics, trace data) |  | QA Analyst | [Enter Date] | MET ✔
4 | EC-ST-04 | ST test cases reviewed, baselined and loaded in test management tool |  | Test Lead | [Enter Date] | MET ✔
5 | EC-ST-05 | Unit test coverage ≥ 80% confirmed by Dev team |  | Dev Lead | [Enter Date] | MET ✔
6 | EC-ST-06 | Known P1/P2 defects from unit testing resolved or waived |  | Dev Lead | [Enter Date] | MET ✔
7 | EC-ST-07 | Test infrastructure: agent simulators, mock integrations configured |  | DevOps | [Enter Date] | MET ✔
8 | EC-ST-08 | Smoke test (sanity suite) passed with ≥ 95% pass rate |  | QA Lead | [Enter Date] | MET ✔
ST — EXIT CRITERIA
# | Criteria ID |  | Owner | Date Verified | Status
1 | EX-ST-01 | Test execution ≥ 98% of planned test cases executed |  | QA Lead | [Enter Date] | MET ✔
2 | EX-ST-02 | Overall pass rate ≥ 95% |  | QA Lead | [Enter Date] | MET ✔
3 | EX-ST-03 | Zero open P1 (Critical) defects |  | Dev Lead | [Enter Date] | MET ✔
4 | EX-ST-04 | Zero open P2 (Major) defects |  | Dev Lead | [Enter Date] | MET ✔
5 | EX-ST-05 | All test execution results documented in test management tool |  | Test Lead | [Enter Date] | MET ✔
6 | EX-ST-06 | Defect triage complete; all defects triaged and assigned |  | QA Lead | [Enter Date] | MET ✔
7 | EX-ST-07 | ST closure report approved by Test Manager |  | Test Manager | [Enter Date] | MET ✔
SIT — ENTRY CRITERIA
# | Criteria ID |  | Owner | Date Verified | Status
1 | EC-SIT-01 | ST exit criteria met and ST closure report signed off |  | Test Manager | [Enter Date] | MET ✔
2 | EC-SIT-02 | SIT environment provisioned; all MVP-1 & MVP-2 integrations configured |  | DevOps | [Enter Date] | MET ✔
3 | EC-SIT-03 | End-to-end integration scenarios reviewed and baselined |  | QA Lead | [Enter Date] | MET ✔
4 | EC-SIT-04 | External system stubs / real connections verified (Kafka, S3, PagerDuty, Slack) |  | Arch Lead | [Enter Date] | MET ✔
5 | EC-SIT-05 | Data migration scripts (if any) verified in lower environment |  | Dev Lead | [Enter Date] | MET ✔
6 | EC-SIT-06 | Performance baseline established from ST phase |  | Perf Engineer | [Enter Date] | MET ✔
7 | EC-SIT-07 | Security scan tools configured on SIT environment |  | SecOps | [Enter Date] | MET ✔
SIT — EXIT CRITERIA
# | Criteria ID |  | Owner | Date Verified | Status
1 | EX-SIT-01 | All end-to-end integration scenarios executed and passed |  | QA Lead | [Enter Date] | MET ✔
2 | EX-SIT-02 | Cross-MVP data flow validated (ingestion → storage → visualization → alert) |  | QA Lead | [Enter Date] | MET ✔
3 | EX-SIT-03 | Zero open P1/P2 defects |  | Dev Lead | [Enter Date] | MET ✔
4 | EX-SIT-04 | Performance test: p95 latency ≤ 200ms; throughput ≥ target |  | Perf Engineer | [Enter Date] | MET ✔
5 | EX-SIT-05 | Security scan complete; no High/Critical vulnerabilities open |  | SecOps | [Enter Date] | MET ✔
6 | EX-SIT-06 | UAT environment seeded; UAT test data prepared |  | QA Lead | [Enter Date] | MET ✔
7 | EX-SIT-07 | SIT closure report approved by stakeholders |  | Test Manager | [Enter Date] | MET ✔
8 | EX-SIT-08 | Leadership sign-off obtained for UAT commencement |  | Leadership | [Enter Date] | MET ✔

## 📋 ST Results
SYSTEM TESTING (ST) — MODULE-WISE RESULTS
MODULE / COMPONENT | 443 | 443 | 427 | 14 | 2 | 0 | Pass % | Fail % | 16 | 12 | PASS | Coverage %
MVP-1: Data Ingestion & Pipeline
Log Collector Agent | 42 | 42 | 40 | 1 | 1 | 0 | 100 | 95.2381 | 2 | 2 | WARN | 0 | 95.2381
Metric Scraper Service | 38 | 38 | 37 | 1 | 0 | 0 | 100 | 97.3684 | 1 | 1 | WARN | 0
Trace Ingestion Pipeline | 35 | 35 | 34 | 1 | 0 | 0 | 100 | 97.1429 | 1 | 1 | WARN | 0
Data Parser & Normalizer | 45 | 45 | 43 | 2 | 0 | 0 | 100 | 95.5556 | 2 | 1 | FAIL | 0
Storage Layer (TimeSeries DB) | 50 | 50 | 48 | 2 | 0 | 0 | 100 | 96 | 2 | 1 | FAIL | 0
API Gateway / Query Service | 40 | 40 | 39 | 1 | 0 | 0 | 100 | 97.5 | 1 | 1 | WARN | 0
MVP-2: Dashboards & Alerting
Dashboard Builder | 48 | 48 | 46 | 2 | 0 | 0 | 100 | 95.8333 | 2 | 1 | FAIL | 0 | 95.8333
Alert Rule Engine | 52 | 52 | 50 | 2 | 0 | 0 | 100 | 96.1538 | 2 | 1 | FAIL | 0
Notification Dispatcher | 38 | 38 | 36 | 1 | 1 | 0 | 100 | 94.7368 | 2 | 2 | WARN | 0
RBAC & Auth Module | 30 | 30 | 30 | 0 | 0 | 0 | 100 | 100 | 0 | 0 | PASS | 0
Platform Admin Console | 25 | 25 | 24 | 1 | 0 | 0 | 100 | 96 | 1 | 1 | WARN | 0
TOTAL | 443 | 443 | 427 | 14 | 2 | 0 | 96.3883 | 3.1603 | 16 | 12 | SUMMARY

## 📋 SIT Results
SYSTEM INTEGRATION TESTING (SIT) — INTEGRATION SCENARIO RESULTS
INTEGRATION SCENARIO | 181 | 181 | 175 | 5 | 1 | 0 | Pass % | Fail % | 6 | 6 | PASS | Coverage %
MVP-1 × MVP-2 End-to-End Integration Scenarios
Log Ingestion → Storage → Query API | 20 | 20 | 20 | 0 | 0 | 0 | 100 | 100 | 0 | 0 | PASS | 0
Metric Collection → TimeSeries → Dashboard | 18 | 18 | 17 | 1 | 0 | 0 | 100 | 94.4444 | 1 | 1 | WARN | 0
Trace Pipeline → Visualization | 15 | 15 | 15 | 0 | 0 | 0 | 100 | 100 | 0 | 0 | PASS | 0
Alert Rule → Evaluation → Notification Dispatch | 22 | 22 | 21 | 1 | 0 | 0 | 100 | 95.4545 | 1 | 1 | WARN | 0
RBAC → Dashboard Access Control | 16 | 16 | 16 | 0 | 0 | 0 | 100 | 100 | 0 | 0 | PASS | 0
API Gateway → Multi-tenant Routing | 18 | 18 | 17 | 0 | 1 | 0 | 100 | 94.4444 | 1 | 1 | WARN | 0
Cross-MVP: Correlation Engine | 20 | 20 | 19 | 1 | 0 | 0 | 100 | 95 | 1 | 1 | WARN | 0
External Integrations (Kafka/S3/PagerDuty) | 25 | 25 | 24 | 1 | 0 | 0 | 100 | 96 | 1 | 1 | WARN | 0
Performance Under Load (1K agents) | 12 | 12 | 12 | 0 | 0 | 0 | 100 | 100 | 0 | 0 | PASS | 0
Failover & Recovery Scenarios | 15 | 15 | 14 | 1 | 0 | 0 | 100 | 93.3333 | 1 | 1 | WARN | 0
TOTAL | 181 | 181 | 175 | 5 | 1 | 0 | 96.6851 | 2.7624 | 6 | 6 | SUMMARY

## 🐛 Defect Tracker
DEFECT TRACKER — MODULE-LEVEL ¦ ST · SIT PHASES
Defect ID | Phase | Module / Component | Scenario / TC ID | Priority | Severity | Status | Assigned To | Description / Summary | Root Cause | Resolution | Target Fix Release | Found Date | Closed Date | Remarks | DEFECT SUMMARY
DEF-001 | ST | Log Collector Agent | TC-ST-015 | P2 | Major | Closed | Dev-A | Memory leak under 10K log/sec sustained load | Resource mgmt bug | Fixed – GC tuning applied | v1.0 | [Date] | [Date] | Verified in regression | Metric | Count
DEF-002 | ST | Metric Scraper Service | TC-ST-028 | P2 | Major | Closed | Dev-B | Scrape interval drift when >500 targets | Timer precision issue | Fixed – scheduler refactored | v1.0 | [Date] | [Date] |  | Total Defects Raised | 14
DEF-003 | ST | Data Parser & Normalizer | TC-ST-042 | P3 | Minor | Closed | Dev-C | Malformed JSON log not producing error event | Edge case handling | Fixed – added schema validation | v1.0 | [Date] | [Date] |  | P1 – Critical | 0
DEF-004 | ST | Storage Layer | TC-ST-056 | P2 | Major | Closed | Dev-D | Query latency spike at 95th percentile > 500ms | Missing index on tenant_id + timestamp | Fixed – composite index added | v1.0 | [Date] | [Date] |  | P2 – Major | 7
DEF-005 | ST | API Gateway | TC-ST-063 | P3 | Minor | Closed | Dev-A | Rate limiting header not returned on 429 response | Response builder bug | Fixed | v1.0 | [Date] | [Date] |  | P3 – Minor | 7
DEF-006 | ST | Dashboard Builder | TC-ST-078 | P2 | Major | Closed | Dev-E | Time range picker resets on panel refresh | State management bug | Fixed – Redux state refactored | v1.0 | [Date] | [Date] |  | P4 – Cosmetic | 0
DEF-007 | ST | Alert Rule Engine | TC-ST-091 | P2 | Major | Closed | Dev-F | Duplicate alerts fired on alert rule re-evaluation | De-duplication logic missing | Fixed – added fingerprint hash | v1.0 | [Date] | [Date] |  | Status: Closed | 11
DEF-008 | ST | Notification Dispatcher | TC-ST-102 | P3 | Minor | Open | Dev-G | PagerDuty webhook retry not honoring backoff | Retry logic issue | Fix in progress | v1.1 | [Date] | — | Deferred to v1.1 | Status: Open | 3
DEF-009 | ST | Log Collector Agent | TC-ST-018 | P3 | Minor | Closed | Dev-A | Agent startup delay 8s vs expected 5s | Dependency init order | Fixed | v1.0 | [Date] | [Date] |  | Status: In Progress | 0
DEF-010 | SIT | Alert → Notification | TC-SIT-024 | P2 | Major | Closed | Dev-F | Alert not dispatched to Slack on resolution event | Event type filter bug | Fixed | v1.0 | [Date] | [Date] |  | Closure Rate % | 0
DEF-011 | SIT | Metric → Dashboard | TC-SIT-031 | P3 | Minor | Closed | Dev-E | Dashboard not refreshing on metric data lag > 30s | Polling interval config | Fixed – reduced polling | v1.0 | [Date] | [Date] |  | ST Phase Defects | 9
DEF-012 | SIT | API Gateway Routing | TC-SIT-045 | P3 | Minor | Open | Dev-B | Multi-tenant header missing in downstream trace context | Propagation gap | Scheduled for v1.1 | v1.1 | [Date] | — | Deferred to v1.1 | SIT Phase Defects | 5
DEF-013 | SIT | Failover Recovery | TC-SIT-058 | P2 | Major | Closed | Dev-D | Write-ahead log replay fails after ungraceful shutdown | WAL corruption scenario | Fixed – WAL checksum validation | v1.0 | [Date] | [Date]
DEF-014 | SIT | Correlation Engine | TC-SIT-061 | P3 | Minor | Open | Dev-C | Trace-to-log correlation shows <5% false positives | Heuristic tuning needed | Planned for v1.1 | v1.1 | [Date] | — | Accepted risk – cosmetic

## 🔴 Outstanding Issues
OUTSTANDING ISSUES — DEFERRED TO UPCOMING RELEASES
⚠ Issues listed below are ACCEPTED RISKS / DEFERRED ITEMS. None block Go-Live. Each has an assigned target release and owner.
Issue ID | Phase | Module / Area | Defect Ref | Priority | Impact | Category | Description | Workaround Available | Risk Level | Target Release | Owner | Accepted By
OI-001 | ST | Notification Dispatcher | DEF-008 | P3 | Low | Enhancement | PagerDuty webhook retry does not honour exponential backoff; manual retry works | Yes – manual retry | Low | v1.1 | Dev-G | QA Lead
OI-002 | SIT | API Gateway | DEF-012 | P3 | Medium | Technical Debt | Multi-tenant trace context propagation header missing in downstream calls; affects distributed tracing completeness | Partial – tracing still functional | Medium | v1.1 | Dev-B | Arch Lead
OI-003 | SIT | Correlation Engine | DEF-014 | P3 | Low | Optimisation | Trace-to-log correlation shows <5% false-positive rate; heuristic model needs tuning | No workaround needed – cosmetic | Low | v1.1 | Dev-C | QA Lead
OI-004 | ST | Dashboard Builder | N/A | P4 | Low | UX Enhancement | Panel colour theme does not persist on browser refresh in Firefox | Yes – refresh once | Low | v1.2 | Dev-E | PM
OI-005 | ST | RBAC Module | N/A | P4 | Low | Enhancement | Bulk user import via CSV limited to 500 rows; workaround is batch upload | Yes – batch upload | Low | v1.2 | Dev-A | PM
OI-006 | SIT | Alert Rule Engine | N/A | P3 | Low | Performance | Alert evaluation latency at 98th percentile is 320ms vs target 200ms under extreme load (5K rules) | Acceptable at current scale | Medium | v1.1 | Dev-F | Perf Engineer
OI-007 | ST | Platform Admin Console | N/A | P4 | Low | Enhancement | Audit log export limited to 90 days in UI; full export via API works correctly | Yes – use API export | Low | v1.2 | Dev-D | QA Lead
OI-008 | SIT | Metric Scraper | N/A | P3 | Low | Stability | Occasional 503 returned from scrape endpoint when target list reloads; auto-recovers in <5s | Auto-recovers | Low | v1.1 | Dev-B | QA Lead
DEFERRED ISSUE PLAN — RELEASE ROADMAP
Target Release | Count of Issues | P2 Count | P3 Count | P4 Count | Estimated Effort (days) | Owner
v1.1 (Next Sprint) | 5 | 0 | 5 | 0 | 5-8 | Dev Lead | All Medium-risk items
v1.2 (Next Cycle) | 3 | 0 | 0 | 3 | 3-4 | Dev Lead | Low-risk UX improvements

## ✅ UAT Entry Criteria
UAT ENTRY CRITERIA & ACCEPTANCE CRITERIA — PRE-UAT HANDOVER DOCUMENT
This document confirms IT Testing Closure (ST + SIT) and defines the conditions under which UAT may commence. UAT is to be conducted by the Leadership Team.
📋 IT TESTING STATUS: ST ✔ CLOSED ¦ SIT ✔ CLOSED ¦ UAT ► PENDING COMMENCEMENT ¦ Decision: GO FOR UAT
SECTION 1 — UAT ENTRY CRITERIA (All must be MET before UAT commences)
# | Criteria ID | Entry Criterion |  | Owner | Evidence / Artefact | Target Date | Actual Date | Status
1 | EC-UAT-01 | ST Phase fully closed — pass rate ≥ 95%, zero open P1/P2 |  | Testing | Test Manager | ST Closure Report (this workbook) |  | [Date] | [Date] | MET ✔
2 | EC-UAT-02 | SIT Phase fully closed — all integration scenarios passed, zero open P1/P2 |  | Testing | Test Manager | SIT Closure Report (this workbook) |  | [Date] | [Date] | MET ✔
3 | EC-UAT-03 | UAT environment provisioned, stable, and accessible to leadership team |  | Infrastructure | DevOps | UAT Env URL shared: [Enter URL] |  | [Date] | [Date] | MET ✔
4 | EC-UAT-04 | UAT test data loaded — representative production-like scenarios for Observability Platform |  | Test Data | QA Lead | Test data load confirmation |  | [Date] | [Date] | MET ✔
5 | EC-UAT-05 | Leadership user accounts created with correct roles (Admin / Viewer) and SSO configured |  | Access | DevOps | User provisioning email sent |  | [Date] | [Date] | MET ✔
6 | EC-UAT-06 | UAT test cases available in Jira and shared with UAT participants (links in Section 3) |  | Test Management | Test Lead | Jira UAT Epic: [Enter link] |  | [Date] | [Date] | MET ✔
7 | EC-UAT-07 | UAT test execution guide / user manual distributed to all UAT participants |  | Documentation | Test Lead | Doc link: [Enter URL] |  | [Date] | [Date] | MET ✔
8 | EC-UAT-08 | Known issues / outstanding items brief (deferred to v1.1 / v1.2) shared with leadership |  | Communication | QA Lead | Outstanding Issues sheet (this workbook) |  | [Date] | [Date] | MET ✔
9 | EC-UAT-09 | Walkthrough / demo session conducted with leadership prior to UAT start |  | Communication | PM | Meeting invite / recording link: [Enter] |  | [Date] | [Date] | MET ✔
10 | EC-UAT-10 | Performance & security test reports shared — p95 latency ≤ 200ms, no High/Critical sec findings |  | Quality | Perf & SecOps | Perf report + Security scan report |  | [Date] | [Date] | MET ✔
11 | EC-UAT-11 | Rollback & contingency plan documented and shared with stakeholders |  | Risk | Arch Lead | Runbook: [Enter URL] |  | [Date] | [Date] | MET ✔
12 | EC-UAT-12 | UAT schedule (start date, end date, daily check-in slots) confirmed with leadership |  | Planning | PM | Calendar invite sent |  | [Date] | [Date] | MET ✔
13 | EC-UAT-13 | UAT feedback / defect logging process explained — Jira project + severity guide shared |  | Process | Test Lead | Jira UAT Defect Project: [Enter link] |  | [Date] | [Date] | MET ✔
14 | EC-UAT-14 | Dedicated UAT support contact (QA Lead + Dev on-call) available during UAT window |  | Support | QA Lead | Support channel: [Enter Slack/Teams] |  | [Date] | [Date] | MET ✔
SECTION 2 — UAT ACCEPTANCE CRITERIA (Conditions for UAT PASS & Go-Live Approval)
# | Criteria ID | Acceptance Criterion |  | Threshold / Target | Measurement Method | Priority | Status
1 | AC-UAT-01 | All UAT test cases executed by leadership team |  | Test Execution | 100% of UAT TCs in Jira executed |  | Jira UAT Test Case Execution Report |  |  | Mandatory | PENDING
2 | AC-UAT-02 | UAT pass rate meets minimum threshold |  | Quality Gate | ≥ 90% pass rate across all UAT test cases |  | Jira execution summary dashboard |  |  | Mandatory | PENDING
3 | AC-UAT-03 | Zero Blocker / Critical defects raised during UAT remain open at closure |  | Defect Quality | 0 open Blocker / Critical UAT defects |  | Jira UAT defect filter: Priority=Blocker+Critical, Status≠Closed |  |  | Mandatory | PENDING
4 | AC-UAT-04 | No more than 2 open Major (P2) defects — all must have fix commitment |  | Defect Quality | ≤ 2 open P2 defects with fix date |  | Jira defect report + commitment register |  |  | Mandatory | PENDING
5 | AC-UAT-05 | MVP-1 core flows validated by leadership: log ingestion, metric collection, trace pipeline, query API |  | Functional Coverage | All MVP-1 happy-path scenarios signed off |  | UAT sign-off checklist (Section 4) |  |  | Mandatory | PENDING
6 | AC-UAT-06 | MVP-2 core flows validated: dashboard creation, alert rule fire, notification delivery, RBAC |  | Functional Coverage | All MVP-2 happy-path scenarios signed off |  | UAT sign-off checklist (Section 4) |  |  | Mandatory | PENDING
7 | AC-UAT-07 | End-to-end observability scenario validated: ingest → store → visualise → alert → notify |  | E2E Validation | Full chain validated in UAT environment |  | E2E scenario TC in Jira: [Enter link] |  |  | Mandatory | PENDING
8 | AC-UAT-08 | Leadership team confirms the platform meets stated business requirements |  | Business Acceptance | Positive sign-off from ≥ 3 of 5 stakeholders |  | Leadership sign-off (Section 4 of this sheet) |  |  | Mandatory | PENDING
9 | AC-UAT-09 | Platform usability acceptable — navigation, dashboard UX, alert configuration flow |  | Usability | No critical UX blockers raised |  | UAT feedback form responses |  |  | Desirable | PENDING
10 | AC-UAT-10 | Performance acceptable in UAT — dashboards load < 3s, alerts fire < 30s |  | Performance | Observed in UAT environment during testing |  | Leadership observation + perf validation TC |  |  | Desirable | PENDING
11 | AC-UAT-11 | Data accuracy confirmed — logs/metrics/traces displayed correctly in dashboards |  | Data Integrity | Zero data discrepancy defects at Blocker/Critical |  | Data validation TCs in Jira: [Enter link] |  |  | Mandatory | PENDING
12 | AC-UAT-12 | Security: leadership can access only their authorised tenants / roles (RBAC validation) |  | Security / RBAC | Zero unauthorised access incidents during UAT |  | RBAC test TCs in Jira: [Enter link] |  |  | Mandatory | PENDING
SECTION 3 — UAT TEST CASE REGISTER (Jira Links — replace placeholders with actual Jira URLs)
# | Jira TC ID | Test Case Title | MVP | Module / Feature | Priority | Test Type | Jira Link | Expected Outcome
1 | UAT-TC-001 | Log ingestion from simulated agent — verify logs appear in dashboard |  | MVP-1 | Log Collector | High | Functional | [Paste Jira TC URL] | Logs visible within 30s in log explorer
2 | UAT-TC-002 | Metric collection — verify CPU/Memory metrics on dashboard |  | MVP-1 | Metric Scraper | High | Functional | [Paste Jira TC URL] | Metrics charted correctly with correct labels
3 | UAT-TC-003 | Trace search — query distributed trace and view waterfall |  | MVP-1 | Trace Ingestion | High | Functional | [Paste Jira TC URL] | Trace timeline and spans rendered accurately
4 | UAT-TC-004 | Create a custom dashboard panel (time-series chart) |  | MVP-2 | Dashboard Builder | High | Functional | [Paste Jira TC URL] | Panel created, saved, and persists on reload
5 | UAT-TC-005 | Configure an alert rule (threshold-based) and validate it fires |  | MVP-2 | Alert Rule Engine | Critical | Functional | [Paste Jira TC URL] | Alert fires within 60s of threshold breach
6 | UAT-TC-006 | Validate Slack notification received on alert trigger |  | MVP-2 | Notification | High | Integration | [Paste Jira TC URL] | Slack message received with correct alert details
7 | UAT-TC-007 | Validate PagerDuty incident raised on Critical alert |  | MVP-2 | Notification | High | Integration | [Paste Jira TC URL] | PagerDuty incident created and linked to alert
8 | UAT-TC-008 | RBAC — Viewer role cannot edit dashboards or alert rules |  | MVP-2 | RBAC | Critical | Security | [Paste Jira TC URL] | Edit controls hidden / disabled for Viewer role
9 | UAT-TC-009 | RBAC — Admin creates a new user and assigns Viewer role |  | MVP-2 | RBAC | High | Functional | [Paste Jira TC URL] | User created and can log in with Viewer access
10 | UAT-TC-010 | End-to-end: ingest log → search → pin to dashboard → alert on pattern |  | MVP-1+2 | E2E | Critical | E2E | [Paste Jira TC URL] | All steps complete without error
11 | UAT-TC-011 | Multi-tenant isolation — tenant A cannot see tenant B data |  | MVP-1+2 | RBAC / Multi-tenant | Critical | Security | [Paste Jira TC URL] | Zero cross-tenant data leakage
12 | UAT-TC-012 | Alert suppression / silence — silence rule stops notifications |  | MVP-2 | Alert Engine | Medium | Functional | [Paste Jira TC URL] | Notifications suppressed during silence window
13 | UAT-TC-013 | Dashboard time range filter — changing range updates all panels |  | MVP-2 | Dashboard Builder | Medium | Functional | [Paste Jira TC URL] | All panels refresh to reflect selected time range
14 | UAT-TC-014 | Audit log — admin actions appear in audit trail |  | MVP-2 | Admin Console | Medium | Compliance | [Paste Jira TC URL] | Audit log entry created for each admin action
15 | UAT-TC-015 | Performance — dashboard with 10 panels loads within 3 seconds |  | MVP-2 | Dashboard Builder | High | Performance | [Paste Jira TC URL] | Page load < 3s observed by UAT participant
SECTION 4 — LEADERSHIP SIGN-OFF — AUTHORISATION TO COMMENCE UAT
By signing below, each stakeholder confirms: (a) IT Testing Closure criteria have been reviewed and accepted, (b) UAT Entry Criteria are met, and (c) UAT may formally commence.
# | Stakeholder Name | Designation | MVP / Area | Date of Review | Authorisation Decision | Comments
1 | [Name] | CTO / VP Engineering | Overall Release — MVP-1 & MVP-2 | [Date] | AUTHORISED ✔
2 | [Name] | Product Owner | MVP-1: Data Ingestion & Pipeline | [Date] | AUTHORISED ✔
3 | [Name] | Product Owner | MVP-2: Dashboards & Alerting | [Date] | AUTHORISED ✔
4 | [Name] | Platform Architect | Architecture & Non-Functional Requirements | [Date] | AUTHORISED ✔
5 | [Name] | Security / Compliance Lead | Security Sign-Off — RBAC, Multi-tenancy | [Date] | AUTHORISED ✔
6 | [Name] | Business Stakeholder / Ops Lead | Business Requirements Traceability | [Date] | AUTHORISED ✔

## 📈 Visualizations
TEST METRICS VISUALIZATIONS — ST · SIT ¦ All Charts Auto-Update
DATA SOURCE (Auto-linked from Results sheets)
Phase/Module | Total | Executed | Passed | Failed | Blocked | Not Run | Priority | Total | Closed | Open | In Progress
ST – MVP-1 | 42 | 42 | 40 | 1 | 1 | 0 | P1 – Critical | 0 | 0 | 0 | 0
ST – MVP-2 | 48 | 48 | 46 | 2 | 0 | 0 | P2 – Major | 7 | 7 | 0 | 0
SIT – All | 181 | 181 | 175 | 5 | 1 | 0 | P3 – Minor | 7 | 4 | 3 | 0
[7 empty] | P4 – Cosmetic | 0 | 0 | 0 | 0

## 📝 Release Notes
RELEASE NOTES v1.0 — OBSERVABILITY PLATFORM ¦ MVP-1 & MVP-2
RELEASE OVERVIEW
Release Version | v1.0
Release Date | [Enter Date]
Release Type | Major – New Platform Launch
MVPs Included | MVP-1: Data Ingestion & Pipeline ¦ MVP-2: Dashboards & Alerting
Test Phases Completed | ST (System Testing) + SIT (System Integration Testing)
Go / No-Go Decision | GO ✔
MVP-1 FEATURES DELIVERED
F-01 | Log Collector Agent – multi-source, multi-format
F-02 | Metric Scraper with Prometheus-compatible pull model
F-03 | Distributed Trace Ingestion (OpenTelemetry compatible)
F-04 | Data Parser & Normalizer with schema registry
F-05 | TimeSeries Storage Layer – multi-tenant partitioned
F-06 | Query API Gateway – REST + GraphQL endpoints
MVP-2 FEATURES DELIVERED
F-07 | Dashboard Builder – drag-and-drop, multi-panel
F-08 | Alert Rule Engine – threshold, anomaly, composite rules
F-09 | Notification Dispatcher – Slack, PagerDuty, Email, Webhook
F-10 | RBAC Module – Admin / Editor / Viewer roles, SSO ready
F-11 | Platform Admin Console – tenant mgmt, audit logs, config
KNOWN LIMITATIONS (v1.0)
L-01 | PagerDuty webhook retry without exponential backoff → Fixed in v1.1
L-02 | Multi-tenant trace context propagation gap → Fixed in v1.1
L-03 | Trace-log correlation <5% false positives → Optimised in v1.1
L-04 | Dashboard theme not persisting in Firefox → Fixed in v1.2
L-05 | Bulk user CSV import limit 500 rows → Extended in v1.2